## Data
Assigned ECU Group | ID | System test category | LeLe responsible | LeLe category | Lessons learned | Name | Assigned ECU | Phase | Defect severity | Error occurrence | Ticket no. supplier | Solution Responsible | Days in phase | Involved I-Step | Target I-Step | Target Week | Defect category | KIFA-comment | Feedback Supplier | Error description | Defect classification | Creation time | Owner | Defect finder | Defect Finder Team | VIN | Closed in version | Substatus | Software Version | Model series | DTC | Visible for | Planned closing version | Lead model | Detected in Release | Blocking reason | Follow-up
GWM_BMS-01 | 1594133 |  |  |  |  | [EM, vWM] [LU] [SP21] [BEV] Popup "No remaining range" is displayed although electric range is too high | GWM_BMS-01 | 01-New | 06-customer irritated | 02-sporadic | 2023091900232 | bmw | 0 | J001-23-11-520 |  |  |  | #PRIO# reject announced, reasign to IDC | Root cause : .test software is 23-11-520-ATS, StatusRestrictionsVWM send invalid value in 23_11, the reason why vwm is restricted will not be displayed in software 23-11, pop-up is not related to vwm The signal StatusRestrictionsVWM behaves as expected reject as not PWT issue, confirmed by FX | Testbedingung/ test conditions: Driving Aktion/ Action: Start navigation towards a HPC. Beobachtetes Verhalten / observed behavior: Popup „No remaining range“ comes, even though the range was still 121 km. Erwartetes Verhalten / expected behavior: No popup „No remaining range“ comes, given the range is 121 km. Reproduzierbarkeit/Reproducibility: reproducible Häufigkeit/Frequency: sporadic Bewertung/Rating: BI-6 ------------------------------------------------------------ Fahrzeug/Vehicle: J01 Fahrzeugdaten/Vehicledata: 137146 Motor: BEV ------------------------------------------------------------ Auftretenszeitpunkt: 15.09.2023, 14:08 \\europe.bmw.corp\BRIAN\DE-MUC\EG\EM\EG-029\J001\TA10021\20230915_1459\xoraya_000118\converted Alexandru Tone, EA-PbM, 19.09.2023: Forward to GWM. 2023-09-19; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. 20.09.2023, Christoph Hauner, EC-EA-4: Informationen zum Tolerated Prozess/Schiebeticketprozess Wirkkettenübergreifende Fehlerbeschreibung aus CoC Sicht / Ursache // Error Description from CoC point of view:Start navigation towards a HPC.Beobachtetes Verhalten / observed behavior:Popup „No remaining range“ comes, even though the range was still 121 km.Erwartetes Verhalten / expected behavior:No popup „No remaining range“ comes, given the range is 121 km.Häufigkeitsprognose / Felddatenanalyse für Entwicklung, Qualitätsarbeit undAnforderungsauslegung / Fehlerheilung // Failure Occurance / Healing Condition:sporadic, healing condition: no healing conditionKundenauswirkung // impact for customer: in the described use case the customer gets a wrong CCM "no remaining range", even though he has 121 km leftAnweisung für Werksprozesse // Impact for plant:no impactAnweisung für Handelsorganisation // impact for service: no impactZiel Fachabteilung / Recommendation from Department: Shift to 24-03Expertenrunde 21.09.2023(R. Simonsen, EC-EE-4, S.Herrmann, EC-EA-4, L.Gerisch, EE-8-A, J.Aigner, CA-610) kein Schieben auf 24-03, Ticket wird an MGU rejected. | Homologation L-labelled, No_Showstopper_Confirmed | 2023-09-19 06:55 | Julian Requejo | Bastian Buchauer | [AT]Energiemanagement | V137146 |  | Appointment | 0000B0D5 010.000.005 | J01 |  |  |  | J01 |  | Not responsible
GWM_MCU-01 | 1591393 |  |  |  |  | [J01]#GWM_MCU-01# ERROR_INTERPRETATION After Sending the Diagnose Job FS_LESEN_DETAIL with argument as hexadecimal DTC code from the 'GWM_MCU1' SGBD | GWM_MCU-01 | 01-New | 04-deficient | 04-reproducable |  | bmw | 0 | J001-24-07-430 |  |  | Systemfunktionen | Duplicate to 1553904 suspected |  | platform (e.g. BBG, FAT, TSP, Simulation,...): Spotlight_Labcar_BJ Y number: D0102C VIN Number: WMW51GC080HY06884 Time:problem find time:2023-09-14 15:37(China time UTC:+8).- Problem finder : Zhao Yalu, (Yalu.Zhao@partner.bmwgroup.com) preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): ACTION: 1. Switch to PWF state "PAD" 2. Evaluate suitable SGBD via SGBD-Index 3. Sending the Diagnose Job FS_LESEN from the 'GWM_MCU1' SGBD 4. check if FS_LESEN has entries 5. Sending the Diagnose Job FS_LESEN_DETAIL with argument as hexadecimal DTC code ('0x23fad4') from the 'GWM_MCU1' SGBD expected result/behaviour: JOB_STATUS: OKAY observed result/behaviour: ERROR_INTERPRETATION possible impact: NO actions/steps to recover from error: NO test case reference: Manual Run 8227093 - DTM_EE_Spotlight_R-23-08_J01-24-07_[Sys_Basis_DIAG3] Standard diagnosis extended [01.05.03.06.03.04]_GWM_MCU-01 14.09.2023, Yalu.Zhao. EC-EE-5 I retested the case by EDIABAS and it still failed. The screenshots and Prg file have uploaded. Please help check and analyze. Thanks. Alexandru Tone, EA-PbM, 15.09.2023: Forward to GWM. 19.09.2023, Yalu.Zhao. EC-EE-5 The Defect 1553904 is for J05-24-03-480, but this Defect is for J01-24-07-430. Although the PDX is same, but SWFL and SWFK is different between J05 and J01. So this Defect is still a issue. 2023-09-22; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake with EA-220. 2023-09-25; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake accepted by EA-220. 2023-09-25; A. Berna, EA-230: Referenz stelle ist nachgefragt von meiner Seite kann ich keinen Fehler finden 2023-09-25 A.Berna, EA-230: zur Analyse benötigen wir folgenden Daten / Informationen: api.trc (nur von dem Fehlerfall)ifh.trc (nur von dem Fehlerfall) |  | 2023-09-14 10:42 | Julian Requejo | Yalu Zhao | Spotlight_Labcar | WMW51GC080HY06884 |  |  | GWM_MCU__01__21MCU800376U.008_003_005.pdx | J01 |  |  |  | J01 | R-23-08 | Further traces necessary
GWM_VCU-01 | 1574936 |  |  |  |  | SOC range calculation was never done on that trip | GWM_VCU-01 | 01-New | 05-unsatisfactory | 02-sporadic |  | bmw | 8 | J001-23-11-510 |  |  | Application Navigation Korea | #FEV_WS# #PRIO# |  | platform (e.g. BBG, FAT, TSP, Simulation,...): J01BEV_VS1preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): Navigation App ver: 2.2.2Navigation--> Set destination--> Start route guidance--> Check the SOC rangeexpected result/behavior: SOC range calculation must be done immediatellyobserved result/behavior: SOC range calculation was never done on that tripCalculating display (moving two dots) kept shownpossible impact: Feel weirdIrritationactions/steps to recover from error: Cancel route guidance--> Set the same destination again--> RecoveredSometimes this issue could be happenedtest case reference: *Zeitpunkt:* 31.08.2023 [16:04:00] (UTC + 9), 0 km *Melder:* Park Jiryun; EG-8-JP; 273-9926; Jiryun.Park@partner.bmw.co.jp *Problemmanager:* Park Jiryun; EG-8-JP; 273-9926; Jiryun.Park@partner.bmw.co.jp *Fahrt(en):* Von 31.08.2023 [10:34] Uhr, 8335 km bis 31.08.2023 [17:10] Uhr, 8436 km *Fahrzeug:* J01; EUR/JP; E RL; M-DI 973E; WMW12GC01RTA10017; B753922; 137168; *I-Stufe:* J001-23-11-510 *Head Unit:* MGU_02_A; BMW IDC23;pu2311-23w33.4-1-nodex_IDC23_E_23w33.4-1-8;idc23;HWEL:A907-005.001.005 *Ecu:* MGU_02_A; BMW IDC23;pu2311-23w33.4-1-nodex_IDC23_E_23w33.4-1-8;idc23; HWEL:A907-005.001.005 *Map DB:* / *Equipment:* *Connected Drive:* PROD: eMobilityServices(LSC_PHEV, I_NATCHARGGST), remoteServices(RSPP, RCHC, RCHP, RDU, R360_HU, VF, RCN, REMOTE_IN_CAR_DWA, RSVSR, REMOTE_IN_CAR, RLF, RDL, RHB), RemoteServices(RCHP, RCHC, VF_INTERNAL, RSVSR, REMOTE_IN_CAR, REMOTE_IN_CAR_DWA, RCN, RDL, RLF, RHL_INTERNAL, VF, RHB, RDU, RD_INTERNAL, R360_HU), teleServices(TD_ASC, TD_ASC, TD_ASC, TD_ASC, TD_TSBG, TD_TSBG, TD_TSBG, TD_TSBG, TD_HOTLC, RD_INTERNAL, TD_B_CALL, ACALL_AUTOMATIC_MGU, RHL_INTERNAL, ACALL_MANUAL_MGU, VF_INTERNAL, MYINFO_INTERNAL), connectedDriveServices(MYINFO_PUSH), intelligentEmergencyCall(AACN, PSAP), GENERIC_VIN(INCARPAYMENT, INCARPAYMENT, INCARPAYMENT, INCARPAYMENT, CRADIO, CRADIO, CRADIO, CRADIO, SI_FESTIVAL_MODE, SI_FESTIVAL_MODE, SI_FESTIVAL_MODE, SI_FESTIVAL_MODE, FUTURE_DESTINATION, FUTURE_DESTINATION, FUTURE_DESTINATION, FUTURE_DESTINATION, PERSO_GUESTPROTECT, PERSO_GUESTPROTECT, PERSO_GUESTPROTECT, PERSO_GUESTPROTECT, MEDIAENGINE, BMW_LINK_VIEWER, SMART_ACCESS_BASIC, SAFE_SHARE_CAPABLE, ANDROID_PROACTIVITY, ANDROID_WEATHER, SMART_ACCESS_2_ACTIVATION_UWB, THIRDPARTYSTORE, IP_LOCALIZATION, SPEECH_PREMIUM_VISUAL, PREMIUM_WELCOME_SCREEN, MAPS_SATELLITE_IMAGES, MAPS_TRAFFIC_VISUALIZATION, APPS_PREMIUM, MAPS_3D_VISUALIZATION, MAPS_JUNCTION_VIEW, SHOP, JOY_RECORDER_WIFI, ANDROID_AUTO, SI_SMART_WINDOW_OPENER, CARPLAY, PRIVACY_MANAGER, CG_BASE_PLUS, SPEECH_CERENCE_LOCAL, LOCATION_BASED_CHARGING_SETTINGS, DP_SMART_MAINTENANCE_VIS_D-OFF, SPEECH_CERENCE_CLOUD, DRIVE_RECORDER_WIFI, RSU_BASIS, JOY_RECORDER, POI_SEARCH, VWM_3_0, NONDORMANT, IPA_BASE, LSEARCH_APP_GOOGLE_LT, SFA_MASTER, CRM_INFO, AUGMENTEDVIEW_WIDGETACTIVATION, MAPUPDATE_ADAS_L2_BASE, DRIVE_RECORDER_EXPORT, RSU_A4A, AUTO_TIME_SERVICE, SPEECH_THIRD_PARTY_ALEXASDK, HV_WARN, MAPS_ROW, EVENT_RECORDER, CDC_2018, SNAPSHOT, DR_NEXT_APP, EUECALL, CRASH_RECORDER, MAPUPDATE_ADAS_L2, ASSISTEDDRIVINGVIEW_WIDGETACTIVATION, MINI_PERSONAL_PICTURE, TRIP_STATISTICS) *Traces:* \\asiapacific.bmw.corp\BRiAN\JP-TOK\FIT\EG-7FIT_Japa\J001\TA10017\20230831_1625\ Traces were converted with CARMEN 3.x LFC ==> please open the traces for analysis in CARMEN 3.x to get the correct timestamp Access information to the referenced Traces *TraceLab Session:* https://tracelab.bmwgroup.net/sessions/vin/TA10017/timestamp/2023-08-31T16:04 *VFC:* *Trigger:* No *GPS:* 35.65108, 140.058393 === end of error description === 18.09.2023, C.Hauner, EC-EA-4: Showstopper Confirmation round (Y. LeNeindre, GWM, M.Tang, EC-EA-4, S.Herrmann, EC-EA-4): ->Showstoppper_Candidate, maybe related to fixed eRoute topics | Showstopper_Candidate | 2023-09-04 11:43 | Julian Requejo | Jiryun Park | [AT]FIT_LAENDER_JP | WMW12GC01RTA10017 |  |  | BTLD_0000B0CF_014_000_004 SWFL_0000B0E7_017_000_008 SWFK_0000B0E8_017_000_008 CAFD_00009906_007_000_001 | J01 |  | 02-Integration |  | J01 | R-23-06 | Further traces necessary | 2023-10-02 12:43
GWM_VCU-01 | 1576870 |  |  |  |  | CCS1 initializing takes too long time sporadically more than 80 seconds | GWM_VCU-01 | 01-New | 05-unsatisfactory | 02-sporadic | 2023090800144 | bmw | 0 | J001-24-03-480 |  |  |  | #PRIO# | Root cause : ticket is duplicate with Octane 1564005， problem was fixed with 24-03-490ATS reject as duplicate, confirmed by sebastian | Time stamp:-30.08.2023, 09:49 (UTC+9)Preconditions:-J01_V137167-Software reference: 24-03-480 ATS+2-Used charging station information: General issue. Not single charging station issue. But in this case,Manufacturer: Daeyoung CHAEVIModel: DCV-3FT100P-UCLocation: 37.336023, 127.858672 (Munmak SA toward Wonju)Actions/steps to (re-) produce the problem:-Go to the charging station -> Wohnen -> Starting DC charging -> Check DC charging function.Expected result/behavior:-Initializing of DC charging should takes less than 30 seconds by energy transferring.Observed behavior:-Initializing takes 80 seconds according to CARMEN (please take a look attached pre-analysis file).It seems to be error as no communication especially CP state B to CM_SLAC_PARM.REQ (it took 58 seconds according to PLC pcap).And this behavior has been observed with different charger makers and models.Actions/steps to recover from error:-Recovered in next charging attempt. It took less than 30 seconds.Possible impact:-Customer could be unplug charging cable while initializing(for example, after 50 seconds).Software version tested (including supplied software or CAF version if relevant):-VCU.Zeitpunkt:30.08.2023 [09:49:00] (UTC + 9), km Melder:Kim Sangwan; EG-8-KR; ; Sangwan.Kim@partner.bmw.co.kr Problemmanager: Kim Sangwan; EG-8-KR; ; Sangwan.Kim@partner.bmw.co.kr Fahrt(en):Von 30.08.2023 [04:47] Uhr, 10985 km bis 30.08.2023 [10:36] Uhr, 11178 km Fahrzeug:J01; EUR/KR; E ; WMW11GC01RTA10019; B753822; 137167; I-Stufe:J001-24-03-480 Head Unit:MGU_02_A; BMW IDC23;pu2311-23w33.4-1-nodex_IDC23_E_23w33.4-1-8;idc23;HWEL:7D84-005.001.005 Ecu:GWM_VCU1; CAFD:9906-007.000.001_BTLD:BBEA-103.000.001_SWFL:B9E4-104.000.007_SWFK:B9CA-104.000.007; HWEL:9918-006.000.000 Map DB: / Equipment: Connected Drive:INT: intelligentEmergencyCall(PSAP, AACN), teleServices(RD_INTERNAL, ACALL_MANUAL_MGU, ACALL_AUTOMATIC_MGU, MYINFO_INTERNAL, RHL_INTERNAL, VF_INTERNAL, TD_HOTLC, TD_ASC, TD_TSBG, TD_B_CALL, LSC_OTD), RemoteServices(REMOTE_IN_CAR_DWA, REMOTE_IN_CAR, VF, RCHC, RHL_INTERNAL, RDU, R360_HU, RHB, RCN, VF_INTERNAL, RLF, RCHP, RDL, RD_INTERNAL, RSVSR), connectedDriveServices(MYINFO_PUSH), GENERIC_VIN(MINI_PERSONAL_PICTURE, JOY_RECORDER_WIFI, MEDIAENGINE, BMW_LINK_VIEWER, SHOP, ANDROID_PROACTIVITY, ANDROID_WEATHER, ANDROID_AUTO, HV_WARN, MAPUPDATE_ADAS_L2_BASE, CDC_2018, DRIVE_RECORDER_WIFI, CRASH_RECORDER, DRIVE_RECORDER_EXPORT, AUTO_TIME_SERVICE, VWM_3_0, CRM_INFO, JOY_RECORDER, RSU_BASIS, IPA_BASE, LSEARCH_APP_GOOGLE_LT, EVENT_RECORDER, CARPLAY, MAPS_3D_VISUALIZATION, DR_NEXT_APP, SNAPSHOT, SPEECH_CERENCE_LOCAL, MAPUPDATE_ADAS_L2, PRIVACY_MANAGER, MAPS_PREMIUM_POIS, ON_STREET_PARKING, MAPS_TRAFFIC_VISUALIZATION, PERSO_GUESTPROTECT, MAPS_TRAVEL_PLANNING, PERSO_KOREA, MAPS_DAILY_COMMUTE, FUTURE_DESTINATION, SI_FESTIVAL_MODE, MAPS_JUNCTION_VIEW, TRIP_STATISTICS, AUGMENTEDVIEW_WIDGETACTIVATION, SAFE_SHARE_CAPABLE, ASSISTEDDRIVINGVIEW_WIDGETACTIVATION, POI_SEARCH, CG_BASE_PLUS, MAPS_KR, LOCATION_BASED_CHARGING_SETTINGS, RSU_A4A, SPEECH_CERENCE_CLOUD, DP_SMART_MAINTENANCE_VIS_D-OFF, SFA_MASTER, SMART_ACCESS_BASIC, SMART_ACCESS_2_ACTIVATION_UWB), remoteServices(RSPP, RCHC, RHB, RSVSR, RDU, RDL, REMOTE_IN_CAR_DWA, REMOTE_IN_CAR, VF, RCN, RCHP, RLF, R360_HU), eMobilityServices(I_NATCHARGGST, LSC_PHEV) Traces:\\asiapacific.bmw.corp\BRIAN\KR-SEL\EG-7FIT_Kore\J001\TA10019\20230901_1028\ Traces were converted with CARMEN 3.x LFC ==> please open the traces for analysis in CARMEN 3.x to get the correct timestamp Access information to the referenced Traces Other occurrences - 0:TraceLab Session:https://tracelab.bmwgroup.net/sessions/vin/TA10019/timestamp/2023-08-30T09:49 === end of error description === Alexandru Tone, EA-PbM, 08.09.2023: Forward to GWM. 21.09.2023, C.Hauner, EC-EA-4:Showstopper Confirmation round (Y. LeNeindre, GWM, M.Tang, EC-EA-4, S.Herrmann, EC-EA-4, FX.Robert, EC-EA-4): ->Showstopper Candidate until more traces are available 26.09.2023, C.Hauner, EC-EA-4:Showstopper Confirmation round (Y. LeNeindre, GWM, S.Herrmann, EC-EA-4, FX.Robert, EC-EA-4): -> No_Showstoppper_Confirmed, initialisation is working, just takes longer 27.09.2023, C.Hauner, EC-EA-4:reject announced, dupliacte to #1564005 | No_Showstopper_Confirmed | 2023-09-06 11:50 | Julian Requejo | Sangwan Kim | [AT]FIT_LAENDER_KR | WMW11GC01RTA10019 |  | Appointment | CAFD:9906-007.000.001_BTLD:BBEA-103.000.001_SWFL:B9E4-104.000.007_SWFK:B9CA-104.000.007 | J01 |  | 02-Integration |  | J01 | R-23-09 | Child (Duplicate)
GWM_VCU-01 | 1576875 |  |  |  |  | [J01] [ENBN] : AC charging pin hooked, not possible to unlock the charging pin via IDC screen (BMW standard wallbox)(error occurrence: sporadic) | GWM_VCU-01 | 01-New | 04-deficient | 02-sporadic | 2023090800146 | bmw | 0 | J001-24-03-480 |  |  |  | #PRIO# #shift_to_24-03_final | Root cause : Charging Handshake Meeting - 2023.09.20: 1. META couldn't reproduce this issue yet (intensive testing since three days, roughly 50 test per day) --> I: Tianyang LI, GWM 2. check with problem finder in RnD center Beijing, the PF only saw this issue for one time close as single event, which cannot be reproduced. confirmed by sebastian | platform (e.g. BBG, FAT, TSP, Simulation,...): VIN:WMW61GC04PG000061 Mode: J01 Timestamp: UTC+8 2023-09-05 13:31 supplier company: BMW standard wallbox city: CN Beijing station: BMW R&D Center (Shunyi) equipmenttype: 3 Phase AC Charging cable Tester contact information: Yu Jiamei (Jiamei.Yu@partner.bmwgroup.com) preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): 1. plug in AC charging cable, and swipe the card to initiate charging, observed that charging not started 2. try to unlock the charging cable by press IDC screen at 13:31 expected result/behaviour: 1. The AC charging pin go back and unlock the charging cable observed result/behaviour: 1. The AC charging pin cannot go back and still lock the charging cable 2. The vehicle cannot charge 3. Lock the vehicle and then the vehicle start to charge itself at 13:39 Actions/steps to recover from error: 1. None Alexandru Tone, EA-PbM, 08.09.2023: Forward to GWM. 2023-09-08; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. 12.09.2023, C.Hauner, EC-EA-4:Showstopper Priorisierung mit S.Herrmann, EC-EA-4, R.Simonsen, EC-EE-4, F.Wiesbeck, LU-5, J.Requejo, EC-EA-4, C.Ingrisch, EE-LU, L.Haas, EC-EE-4, Y.LeNeindre, GWM:-> probably known issue, no_showstopper_confirmed 13.09.2023, Christoph Hauner, EC-EA-4: Informationen zum Tolerated Prozess/Schiebeticketprozess Wirkkettenübergreifende Fehlerbeschreibung aus CoC Sicht / Ursache // Error Description from CoC point of view:AC Charging GB/Tplug in AC charging cable, and swipe the card to initiate charging, observed that charging not startedtry to unlock the charging cable by press IDC screen at 13:31expected result/behaviour:The AC charging pin go back and unlock the charging cableobserved result/behaviour:The AC charging pin cannot go back and still lock the charging cableHealing:Lock the vehicle and then the vehicle start to charge itselfHäufigkeitsprognose / Felddatenanalyse für Entwicklung, Qualitätsarbeit undAnforderungsauslegung / Fehlerheilung // Failure Occurance / Healing Condition:sporadic, healing condition: lock and unlock the vehicle via keyKundenauswirkung // impact for customer: customer cannot pull the charging cable if he runs into this issue. He has to lock and unlock the vehicle, so that the signal from ODP will be sent again and the charging cable will be unlockedAnweisung für Werksprozesse // Impact for plant:no impactAnweisung für Handelsorganisation // impact for service: no impactZiel Fachabteilung / Recommendation from Department: Shift to 24-03Expertenrunde 14.09.2023(R. Simonsen, EC-EE-4, S.Herrmann, EC-EA-4, T.Mayer, SAT-V-2, J.Puchtinger, EE-8-A, R.Prietzsch, EE-8-A, L.Gerisch, EE-8-A) Schieben auf 24-03, falls single event und nur an einem Fahrzeug Schieben auf 24-07 EC-EE-4 (SAT-A): iO CA-610: iO (RM M.Melcher via Mail) EG-7: iO SAT-V-2: iO EE-8-A: iO AQ-62: iO ES-210 (FO-Laden): iO 26.09.2023, C.Hauner, EC-EA-4: Showstopper Confirmation round (Y. LeNeindre, GWM, S.Herrmann, EC-EA-4, FX.Robert, EC-EA-4): -> No_Showstoppper_Confirmed, single event | Homologation L-labelled, No_Showstopper_Confirmed | 2023-09-06 12:06 | Julian Requejo | Jiamei Yu | EnBn_IuA_CHN_Spotlight | WMW61GC04PG000061 |  | Appointment | GWM_VCU__01__21VCU800384G.017_000_009.pdx | J01 |  |  |  | J01 |  | Further traces necessary
GWM_VCU-01 | 1576944 |  |  |  |  | Charging time forecast deviates very significantly and approaches after adjusted target SOE | GWM_VCU-01 | 01-New | 04-deficient | 01-single event | 2023090700133 | bmw | 1 | J001-23-11-520 |  |  |  | #PRIO# #Shift_to_24-03_final | Root cause : same with Octane 1498931, ticket will be fixed with 24-03-490SF reject as duplicate, confirmed by sebastian | platform (e.g. BBG, FAT, TSP, Simulation,...): V139259 J01 SE ECE VS2/PT2 vehicle preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): The vehicle hangs on the charger and is being charged. expected result/behaviour: The current charging time forecast is plausible and not just after adjusted the target SOE. observed result/behaviour: The vehicle is connected at the hypercharger with a charging power of 74 kW, actual SOE is 68%, target SOE 80% and charging forecast time about 21:00 time. The target SOE will change to 75% and the charging forecast time is changing to time 15:20. After that the SOE is change to 100% and the forecast time is changig to 16:00. Afterwards the SOE will change again to the starting value 80% and the time is changing to 15:25. ---> see Video possible impact: Customer is confused between the difference about more than 5 hours actions/steps to recover from error: test case reference: WE-Fahrt J01 KW35_ V139259_ 01_09_2023.msg 03.09.2023 15:15V139249_2023-09-03[14.59.11]_2023-09-03[15.15.13]_96V139249_2023-09-03[15.15.13]_2023-09-03[15.26.37]_97=== end of error description === Alexandru Tone, EA-PbM, 07.09.2023: Forward to GWM. 2023-09-07; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. 11.09.2023, Christoph Hauner, EC-EA-4: Informationen zum Tolerated Prozess/Schiebeticketprozess Wirkkettenübergreifende Fehlerbeschreibung aus CoC Sicht / Ursache // Error Description from CoC point of view:The vehicle hangs on the charger and is being charged.expected result/behaviour:The current charging time forecast is plausible and not just after adjusted the target SOE.observed result/behaviour:The vehicle is connected at the hypercharger with a charging power of 74 kW, actual SOE is 68%, target SOE 80% and charging forecast time about 21:00 time.The target SOE will change to 75% and the charging forecast time is changing to time 15:20. After that the SOE is change to 100% and the forecast time is changig to 16:00. Afterwards the SOE will change again to the starting value 80% and the time is changing to 15:25-> known issues with charging time estimationHäufigkeitsprognose / Felddatenanalyse für Entwicklung, Qualitätsarbeit undAnforderungsauslegung / Fehlerheilung // Failure Occurance / Healing Condition:reproducable, healing condition: no healing condition needed / mentionedKundenauswirkung // impact for customer: no customer use case, Target SOE will be changed several times during chargingAnweisung für Werksprozesse // Impact for plant:no impactAnweisung für Handelsorganisation // impact for service: no impactZiel Fachabteilung / Recommendation from Department: Shift to 24-03Expertenteam 12.09.2023(R. Simonsen, EC-EE-4, S.Herrmann, EC-EA-4, T.Mayer, SAT-V-2, J.Puchtinger, EE-8-A) Schieben auf 24-03. Ladezeitprognose als Schwerpunkt in 24-03 EC-EE-4 (SAT-A): iO CA-610: iO (RM M.Melcher, CA-610 via Mail) EG-7: iO SAT-V-2: iO EE-8-A: iO AQ-62: iO ES-210 (FO-Laden): iO | No_Showstopper_Confirmed | 2023-09-06 15:14 | Julian Requejo | Sebastian Krafzik | EA-282 | WMW21GC03RTA10124 |  | Appointment | B0E9.018.000.001 | J01 |  |  |  | J01 |  | Child (Duplicate)
GWM_VCU-01 | 1578893 |  |  |  |  | [J05][ENBN]The charging process abort before reach target Soc, without any notification(supplier company: YKC(NIO)) | GWM_VCU-01 | 01-New | 05-unsatisfactory | 01-single event | 2023091100165 | bmw | 9 | J001-24-03-480 |  |  |  | #PRIO# reject anounced | Root cause : comment from BMW Wuke According to the DC can massage the charging stopped artificially the most common causes of artificial stop are : 1) some one stop the charging one the charger, 2)some stop it on phone 3) emergency button be pressed 4) contrl center stop the charge 5) pre-pay account in arrears. also confirmed from the PF this is an single event. after the charging stop he tried multiple times the charging is works well. the single stop comes from EVSE side. so, reject as EVSE issue, confirmed by Wuke | Platform (e.g. BBG, FAT, TSP, Simulation,...): J01-EnBn-CN-vehicle Vin: WMW81GC02PG000083 software vision: GWM_VCU__01__21VCU800384G.017_000_009 time：UTC+8 2023-9-5 13:22 supplier company: YKC(NIO) city: Chongqing station: 蔚来超充站重庆协信星光时代广场 equipmenttype: DC Pile Number: A01172130 Tester contact information: Zhang, Yuning (Yuning.Zhang@partner.bmwgroup.com) Preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): 1. Plug in the charger. 2. Start charging on the mobile phone app. 3. Set Target SOC as 55% Expected result/behaviour: 1. Charging starts 2. Charging stops until reach Target SOC 55% Observed result/behaviour: 1. Charging starts 2. Charging stops at SOC 52% 3. No any related notification or CCM possible impact: Software version. actions/steps to recover from error: can not be recover. test case reference: no test case reference. === end of error description === Alexandru Tone, EA-PbM, 11.09.2023: Forward to GWM. 2023-09-11; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. | Homologation L-labelled, Showstopper_Candidate | 2023-09-07 05:45 | Julian Requejo | Yuning Zhang | EnBn_IuA_CHN_Spotlight | WMW81GC02PG000083 |  | Appointment | GWM_VCU__01__21VCU800384G.017_000_009 | J01, J05 |  |  |  | J05 |  | Not responsible
GWM_VCU-01 | 1581020 |  |  |  |  | [J05][ENBN]charging process was interrupted and reconnected automatically and then repeat this process.(AC charging/supplier company: TELD) | GWM_VCU-01 | 01-New | 06-customer irritated | 04-reproducable | 2023091100162 | bmw | 14 | J001-24-03-480 |  |  |  | #PRIO# | Root cause : after check the trace and talk to the PF the problem is caused by the CC pin of the charger disconnect. due to the PF only find the problem on one charger, the problem should be the charger pin. every time the OBC stop the charging is about 300ms after the CC pin lost. data graphic was attached reject as charging gun issue, confirmed by Wuke | Platform (e.g. BBG, FAT, TSP, Simulation,...): J01-EnBn-CN-vehicle Vin: WMW81GC02PG000083 software vision: GWM_VCU__01__21VCU800384G.017_000_009 time：UTC+8 2023-9-5 12:01, 12:07 supplier company: TELD city: Chongqing station: 重庆南岸区康德国会山一期充电站 equipmenttype: AC Pile Number: 5001080004204 Tester contact information: Zhang, Yuning (Yuning.Zhang@partner.bmwgroup.com) Preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): 1. Plug in the charger. 2. Start charging on the mobile phone app. Expected result/behaviour: 1. Charging starts 2. The charging process runs without problems until it is actively terminated Observed result/behaviour: 1. During the charging process, charging was interrupted 2. "Please re-plug the charging cable, hold and hold for 2 seconds" was displayed in the screen 3. After this, charging restarts. 4. This process was kept repeating. possible impact: Software version. actions/steps to recover from error: can not be recover. test case reference: no test case reference. === end of error description === Alexandru Tone, EA-PbM, 11.09.2023: Forward to GWM. 2023-09-11; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. | Homologation L-labelled, Showstopper_Candidate | 2023-09-07 05:36 | Julian Requejo | Yuning Zhang | EnBn_IuA_CHN_Spotlight | WMW81GC02PG000083 |  | Appointment | GWM_VCU__01__21VCU800384G.017_000_009 | J01, J05 |  |  |  | J05 |  | User Error
GWM_VCU-01 | 1584154 |  |  |  |  | [J05][ENBN]charging failed to start with charging station - Star Charge (DC charging) | GWM_VCU-01 | 01-New | 06-customer irritated | 04-reproducable | 2023090800147 | bmw | 9 | J001-24-03-480 |  |  |  | #PRIO# reject announced | Root cause : The charging is stopped by pressing the "unlock cable now" button on IDC firstly. see picture 2 Then PF tried to re-plug the charging cable for two times, but both of these two actions cannot charge successfully, the charger didn't response BRM message, so our car generate a BRM time out fault. see picture 3 reject as EVSE issue, confirmed by sebastian | Platform (e.g. BBG, FAT, TSP, Simulation,...): J01-EnBn-CN-vehicle Vin: WMW81GC02PG000083 software vision: GWM_VCU__01__21VCU800384G.017_000_009 time：UTC+8 2023-9-7 16:58, 17:03 supplier company: Star Charge city: Chongqing station: 重庆星星充电木洞服务区充电站 equipmenttype: DC Pile Number: 1020353502 Tester contact information: Zhang, Yuning (Yuning.Zhang@partner.bmwgroup.com) Preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): 1. Plug in the charger. 2. Start charging from mobile phone app. 3. Precondition: current SOC was 47%. Expected result/behaviour: 1. Charging start after click "start charging" on the mobile phone. Observed result/behaviour: 1. Charging was not start, "Charging aborted, charging station error" was shown in the HMI. possible impact: customer complain actions/steps to recover from error: can not be recover. test case reference: no test case reference. === end of error description === Alexandru Tone, EA-PbM, 08.09.2023: Forward to GWM. 2023-09-08; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM. 12.09.2023, C.Hauner, EC-EA-4:Showstopper Priorisierung mit S.Herrmann, EC-EA-4, R.Simonsen, EC-EE-4, F.Wiesbeck, LU-5, J.Requejo, EC-EA-4, C.Ingrisch, EE-LU, L.Haas, EC-EE-4, Y.LeNeindre, GWM:-> start charging via Mobile Phone, no_showstopper_confirmed 13.09.2023, C.Hauner, EC-EA-4:reject announced, EVSE issue | Homologation L-labelled, No_Showstopper_Confirmed | 2023-09-07 16:40 | Julian Requejo | Yuning Zhang | EnBn_IuA_CHN_Spotlight | WMW81GC02PG000083 |  | Appointment | GWM_VCU__01__21VCU800384G.017_000_009 | J01, J05 |  |  |  | J05 |  | Not responsible
GWM_VCU-01 | 1590977 |  |  |  |  | FIT-Fahrzeug / VIT-Vehicle D0105E - Overflow tank, hardware: Short of coolant | GWM_VCU-01 | 01-New | 05-unsatisfactory | 01-single event | 2023091900231 | bmw | 1 | J001-23-11-520 |  |  |  |  | Root cause : problem is same with Octane 1520413, it's a showstopper_No issue , only fixed with I-STEP 24-03 465 SF+1. please test it with 24-03-465SF+1 or new SW reject as duplicate, confirmed by Sebastian | platform (e.g. BBG, FAT, TSP, Simulation,...): - observed behaviour occurs on multiple platforms (yes/no): yes observed behaviour occurs in multiple lifecycles (yes/no): no preconditions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): The following DTC occurred in the vehicle TA10027 (J01): 0x23FF99 - Overflow tank, hardware: Short of coolant According to ZEDIS information this DTC gets set when: Fehlersetzbedingungen VoltageSensorCoolantLevel is higher than or equal to 3700mV (calibration) at least 1s (calibration)，VCU shall set overflow tank is short of coolant fault flag to 1. Accoding to Carmen preanalysis.bmp at the time of the DTC recording: The vehicle was in PAD mode and the CCM 568 according to signals GWM_BMS_PosRlySts (AE_CAN_FD) anf GWM_BMS_NegRlySts (AE_CAN_FD) the safe contactor seems to be open also the VoltageSensorCoolantLevel shows way lower values ~1.083,78mV. This defect has been created to see why this DTC was set and if there are any means to solve it. For more traces please use the Brian Link: \ 1920301a016.bmwgroup.net\brian_e19_cn\BeMo_in-tech\J001\TA10027 Zulassung BRiAN Laufwerk (Traces) / Approval BRiAN Drive (Traces): Zul.muc Antrag stellen / New Request Systemzulassung / System Roles BRiAN (Systemname) / BRiAN (System Name) Zulassung als -> Tracefiles lesen (global) / Approval as Read -> Tracefiles (global) Kommentar … / Comment … Systemzulassung beantragen / System Role Request Vehicle handler: Nie Perry (Perry.Nie@partner.bmw.com) expected result/behaviour: No error memory entry observed result/behavior: ---------------------------------------------------------------------------------------------- Steuergerät : 3A EME/CCU - GWM_VCU1 - GWM VEHICLE CONTROL UNIT Job Status : OKAY Fehlerort : 2359193 0x23FF99 - Overflow tank, hardware: Short of coolant Readyness Flag : 16 Test conditions fulfilled Fehler vorhanden : 12 Error not present now, but already stored Warnung Flag : 128 Error would not cause a warning lamp to light up F Überlauf : 0 Fehlerklasse : 256 Plausibility and Functional Diagnosis Häufigkeitszähler : 1 Heilungszähler : 0 Statusbyte : 2E 1. Datensatz Umwelt Anzahl : 137 Umwelt Kilometer : 19957 Umwelt Meter : 19957.272 Umwelt Km insync : 1 Umweltbedingung BN : -1 Umweltbedingung TN : -1 Umwelt Zeit : 7785859 18.09.2023 13:22:58 Umwelt Zeit ms : 420 Umwelt Zeit Supreme: 7785859.420 18.09.2023 13:22:58,929 Umwelt Zeit Insync : 1 Zeit Sync Methode : 0 Sync Methode Info : RelativeTime Zeit User Info : insync, ms ECU overall, not comparable Umweltbedingung 1 : 20480 UWB_CANR_VVehSpd 0 km/h Umweltbedingung 2 : 20481 UWB_CANR_ULvBattAct 12 V Umweltbedingung 3 : 20482 UWB_CANR_NTmRotSpd 0 rpm Umweltbedingung 4 : 20484 UWB_ST_CON_VEH: Check_analysis_diagnostics 7 Umweltbedingung 5 : 20485 UWB_CPT_IOSRV_ADC_PIN52AND39PP_ASW_GET 11865 mV Umweltbedingung 6 : 20486 UWB_CPT_IOSRV_ICU_PIN96PP_ASW_GETFREQUENCY 100.7 Hz Umweltbedingung 7 : 20487 UWB_CPT_IOSRV_ICU_PIN96PP_ASW_GETDUTY 49 % Umweltbedingung 8 : 20488 UWB_CPT_IOSRV_ADC_PIN62PP_ASW_GET 778 mV Umweltbedingung 9 : 20489 UWB_CPT_IOSRV_ADC_PIN61PP_ASW_GET_PIN61 391 mV Umweltbedingung 10 : 20490 UWB_CPT_IOSRV_ADC_PIN9PP_ASW_GET 448 mV Umweltbedingung 11 : 20584 UWB_StatusHighVoltagePlugEDH: In case no statement can be made e.g. 'HV-network not active' 2 Umweltbedingung 12 : 20585 UWB_StatusHighVoltagePlugEKMV: In case no statement can be made e.g. 'HV-network not active' 2 Umweltbedingung 13 : 20586 UWB_CPT_IOSRV_DI_PIN51PP_ASW_GET: Close 1 Umweltbedingung 14 : 20491 UWB_CPT_IOSRV_ADC_PIN16PP_ASW_GET 4025 mV Umweltbedingung 15 : 20492 UWB_CPT_IOSRV_ADC_PIN59PP_ASW_GET 4023 mV Umweltbedingung 16 : 20493 UWB_CPT_IOSRV_ADC_PIN48PP_ASW_GET 4998 mV Umweltbedingung 17 : 20494 UWB_CPT_IOSRV_ADC_PIN44PP_ASW_GET 4999 mV Umweltbedingung 18 : 20495 UWB_CPT_IOSRV_ADC_PIN47PP_ASW_GET 4997 mV Umweltbedingung 19 : 20496 UWB_CPT_IOSRV_ADC_PIN63PP_ASW_GET 4999 mV Umweltbedingung 20 : 20497 UWB_PTCO_TQEMFRNTDMDLIMD 0 Nm Umweltbedingung 21 : 20498 UWB_TDAP_TQWHLACCRPEDLREQ 0 Nm Umweltbedingung 22 : 20499 UWB_CANR_IBATTPACK 0 A Umweltbedingung 23 : 20500 UWB_CANR_UHVBATTACT 437 V Umweltbedingung 24 : 20581 UWB_GWM_BMS_HiVoltInterlockSts: Normal 0 Umweltbedingung 25 : 20582 UWB_GWM_MCU_HIVOLTINTERLOCKSTS: Normal 0 Umweltbedingung 26 : 20583 UWB_GWM_ODP_HiVoltInterlockSts: Normal 0 Umweltbedingung 27 : 20587 UWB_MonCANT_WtrPmpTwoFltLvl: on 1 Umweltbedingung 28 : 20501 UWB_CANR_SOCBATTTRAC 79.5 % Umweltbedingung 29 : 20502 UWB_CANR_PWRBMSSOEBATT 39.5 kWh Umweltbedingung 30 : 20503 UWB_CANR_PWRCMPRACT 0 kW Umweltbedingung 31 : 20504 UWB_CANR_PWREDHACT 0 kW Umweltbedingung 32 : 20505 UWB_CANR_IFRNTMTR 0 A Umweltbedingung 33 : 20506 UWB_CANR_UEM2HVSIDE 14 V Umweltbedingung 34 : 20507 UWB_GWM_MCU_ACTTRQ 0 Nm Umweltbedingung 35 : 20508 UWB_MCU_MOTORPOWER 0 kW Umweltbedingung 36 : 20509 UWB_VMCO_TQWHLFRNTFASTESPDMD 0 Nm Umweltbedingung 37 : 20510 UWB_CANR_TBATTINLETWTR 26 °C Umweltbedingung 38 : 20598 UWB_ 68 % Umweltbedingung 39 : 20599 UWB_LINR_ValPump1ActOpen 68 % Umweltbedingung 40 : 20600 UWB_TMCO_PctgPmpTwo 0 % Umweltbedingung 41 : 20601 UWB_LINR_PctgWtrPmpTwoRunSpd 0 % Umweltbedingung 42 : 20602 UWB_TMCO_StepAgsOpen 16392 Umweltbedingung 43 : 20511 UWB_CANR_UOBCCHRGOUTP 15.2 V Umweltbedingung 44 : 20512 UWB_CANR_IOBCOUTD 0 A Umweltbedingung 45 : 20513 UWB_EVCC_EVSEPRESVOLT 0 V Umweltbedingung 46 : 20514 UWB_EVCC_EVSEPRESCURR 0 A Umweltbedingung 47 : 20515 UWB_CHDP_ITARCHRGN 0 A Umweltbedingung 48 : 20516 UWB_CHDP_UTARCHRGN 0 V Umweltbedingung 49 : 20517 UWB_SRCH_TACCHRGNSNSR1 0 °C Umweltbedingung 50 : 20518 UWB_SRCH_TACCHRGNSNSR2 0 °C Umweltbedingung 51 : 20519 UWB_SRCH_TACCHRGNSNSR3 0 °C Umweltbedingung 52 : 20520 UWB_SRCH_TACCHRGNSNSR4 0 °C Umweltbedingung 53 : 20603 UWB_LINR_StepAGSActOpenVal 16392 Umweltbedingung 54 : 20604 UWB_FWV_VoltSts: Voltage ok 0 Umweltbedingung 55 : 20483 UWB_SrAP_PctgAccrPosn 0 % Umweltbedingung 56 : 20521 UWB_CANR_TCABLEENTR1 27 °C Umweltbedingung 57 : 20522 UWB_CANR_TCABLEENTR2 27 °C Umweltbedingung 58 : 20523 UWB_CANR_TCABLEENTR3 27 °C Umweltbedingung 59 : 20524 UWB_CANR_TCABLEENTR4 27 °C Umweltbedingung 60 : 20525 UWB_CANR_TQWHLGUIDANCETAR -20000 Nm Umweltbedingung 61 : 20526 UWB_TDVL_TQWHLMAXSPDLIM 0 Nm Umweltbedingung 62 : 20527 UWB_SRCH_TDCCHRGNSNSR1 27 °C Umweltbedingung 63 : 20528 UWB_SRCH_TDCCHRGNSNSR2 27 °C Umweltbedingung 64 : 20529 UWB_CPT_IOSRV_ADC_PIN64_CC21PP_ASW_GET 4998 mV Umweltbedingung 65 : 20530 UWB_CPT_IOSRV_DI_PIN11PP_ASW_GET: Low 0 Umweltbedingung 66 : 20531 UWB_CPT_IOSRV_DI_PIN93PP_ASW_GET: High 1 Umweltbedingung 67 : 20532 UWB_TMCO_bFANRlyCtrl: off 0 Umweltbedingung 68 : 20533 UWB_CPT_IOSRV_DI_PIN31PP_ASW_GET: close 1 Umweltbedingung 69 : 20534 UWB_TMCO_bWtrPmpRlyCtrl: on 1 Umweltbedingung 70 : 20535 UWB_ETCo_StElecSys: ETCO_STELEC_OFF 0 Umweltbedingung 71 : 20536 UWB_ETEM2_ModEm2Req: ETEM2_EM2MODREQ_WOBAT 7 Umweltbedingung 72 : 20537 UWB_ETDC_StDcdcOperMod: ETEM2_EM2MODREQ_STB 0 Umweltbedingung 73 : 20538 UWB_ETCh_StChrgnSts: ETCH_STCHRGNSTS_NOCHRGN 0 Umweltbedingung 74 : 20539 UWB_DTCN_NRDTC1: Less severe error 292 Umweltbedingung 75 : 20540 UWB_DTCN_NRDTCHIST: Moderate error 127 Umweltbedingung 76 : 20541 UWB_MonFltM_StVCUFltLvlSum: Level_4 4 Umweltbedingung 77 : 20542 UWB_FltM_StSysFltLvl: Level_4 4 Umweltbedingung 78 : 20543 UWB_FltM_StSysFltLmp: Red_lamp_ON 2 Umweltbedingung 79 : 20544 UWB_FltM_StsActvnCCMID: Invalid value 516 Umweltbedingung 80 : 20545 UWB_GWM_BMS_SysFaultLvl: No_error 0 Umweltbedingung 81 : 20546 UWB_SrDM_StDrvMod: comfort 2 Umweltbedingung 82 : 20547 UWB_SrGL_StGearPosn: P 1 Umweltbedingung 83 : 20548 UWB_SRGL_STBRKSTS: No_active 0 Umweltbedingung 84 : 20549 UWB_SrGL_StEparkReq: ETCO_STELEC_OFF 3 Umweltbedingung 85 : 20550 UWB_GWM_BMS_PosRlySts: open 0 Umweltbedingung 86 : 20551 UWB_GWM_BMS_NegRlySts: open 0 Umweltbedingung 87 : 20552 UWB_ST_AH: AutoH activated and does not hold vehicle 1 Umweltbedingung 88 : 20553 UWB_VSC_StsDirjudge: VSC_STSDIR_STDSTL 0 Umweltbedingung 89 : 20554 UWB_GWM_BMS_Sts: Shutdown 6 Umweltbedingung 90 : 20555 UWB_GWM_MCU_OperMod: Afterrun 8 Umweltbedingung 91 : 20556 UWB_GWM_MCU_FailSts: No_error 0 Umweltbedingung 92 : 20557 UWB_CANR_StObcAct: ETEM2_EM2MODREQ_STB 2 Umweltbedingung 93 : 20558 UWB_CANR_StOBCFltLvl: No_error 0 Umweltbedingung 94 : 20559 UWB_CANR_StObcChrgrCnct: Unplugged 0 Umweltbedingung 95 : 20560 UWB_CANR_StDcdcAct: CANR_STDCDC_STB 2 Umweltbedingung 96 : 20561 UWB_CANR_StDCFltLvl: No_error 0 Umweltbedingung 97 : 20562 UWB_CANR_bEparkFltSts: Normal 0 Umweltbedingung 98 : 20564 UWB_TDEC_bCrpEna: disable 0 Umweltbedingung 99 : 20565 UWB_CANR_StsWhlLvlGuidanceTarTq: CANR_TARTQ_NOTIMPLEMENT 1 Umweltbedingung 10 : 20566 UWB_EVCC_StChrgrCnct: EVCC_STCHRGR_NOTCNCT 0 Umweltbedingung 10 : 20567 UWB_SrGL_StEpbActvReq: SrGL_EPBACTVREQ_ZERO 0 Umweltbedingung 10 : 20568 UWB_CANR_IdSbwmGearShiftPosn: CANR_SHIFT_ZERO 0 Umweltbedingung 10 : 20569 UWB_CANR_StsSbwmParkBtnReq: SrGL_EPBACTVREQ_ZERO 0 Umweltbedingung 10 : 20570 UWB_CANR_StIBEpark: No_request 0 Umweltbedingung 10 : 20571 UWB_TDAP_bMcuPrkgCtrlReq: Not active 0 Umweltbedingung 10 : 20572 UWB_TDVL_bMaxSpdLmtAct: Active 1 Umweltbedingung 10 : 20573 UWB_EVCC_StELockMotPosn: EVCC_STELOCKPOSN_UNLCK 0 Umweltbedingung 10 : 20574 UWB_ETHV_StBms: ETHV_STBMS_SHTDWNFINSH 8 Umweltbedingung 10 : 20575 UWB_VMod_StopChrgReaCan: ETHV_STBMS_IDLE 0 Umweltbedingung 11 : 20576 UWB_EVCC_StChrgnInt: ETHV_STBMS_SHTDWNFINSH 48 Umweltbedingung 11 : 20577 UWB_EVCP_StHndShk: Sleep 0 Umweltbedingung 11 : 20578 UWB_FltM_StVCUHVIL: Normal 0 Umweltbedingung 11 : 20579 UWB_CANR_StsEparkPosn: P 0 Umweltbedingung 11 : 20580 UWB_VMod_StHeat: init 0 Umweltbedingung 11 : 20588 UWB_GWM_BMS_ChargeSysFaultLvl: No_error 0 Umweltbedingung 11 : 20589 UWB_VMod_StopChrgReaVal: InhbAcChrg 0 Umweltbedingung 11 : 20590 UWB_VMod_StInhbPwrSum: Signal_unbefuellt 15 Umweltbedingung 11 : 20591 UWB_VMod_bChrgStrtReq: False 0 Umweltbedingung 11 : 20592 UWB_TMCO_PctgFANOpenCtrl 0 % Umweltbedingung 12 : 20593 UWB_LINR_ValFanActOpen 0 % Umweltbedingung 12 : 20594 UWB_FWV_FaultSts: No error 0 Umweltbedingung 12 : 20595 UWB_FWV_TempSts: No error 0 Umweltbedingung 12 : 20596 UWB_TMCO_PctgFWVVlvReqOutp 69 % Umweltbedingung 12 : 20597 UWB_LINR_ValFourValvActOpen 68.8 % Umweltbedingung 12 : 20605 UWB_BSW_UPpLineTyp1 490 mV Umweltbedingung 12 : 20606 UWB_BSW_UPpLine 1117 mV Umweltbedingung 12 : 20607 UWB_BSW_UDcChrgnFlap 3374 mV Umweltbedingung 12 : 20608 UWB_BSW_USwtM 11049 mV Umweltbedingung 12 : 20609 UWB_BSW_USwtK 2004 mV Umweltbedingung 13 : 20610 UWB_BSW_UCpLine 1571 mV Umweltbedingung 13 : 20611 UWB_BSW_DutyCpLine 0 % Umweltbedingung 13 : 20612 UWB_BSW_FrqCpLine 0 kHz Umweltbedingung 13 : 20613 UWB_SrCh_StsSwtM: unknown 0 Umweltbedingung 13 : 20614 UWB_SrCh_StsSwtK: ETCO_STELEC_OFF 2 Umweltbedingung 13 : 20615 UWB_SrCs_StCrashFailRson: No fault 0 Umweltbedingung 13 : 20616 UWB_GWM_VCU_ThrmMngtDmd: Invalid value 255 Umweltbedingung 13 : 20617 UWB_GWM_VCU_ThrmMngtDmdAdj: Invalid value 255 ---------------------------------------------------------------------------------------------- 3A EME/CCU GWM_VCU1 5.002 G_CCU ------ 1 Hardware (Elektronik) 00009D3C 006.000.000 11.09.2023 GWM VEHICLE CONTROL UNIT 3A EME/CCU 6 Bootloader 0000B0CF 014.000.004 3A EME/CCU 8 Software ECU Speicherimage 0000B0E7 018.000.001 3A EME/CCU 13 BEGU: Detaillierung auf SWE-Ebene 0000B0E9 018.000.001 3A EME/CCU 5 Codierdaten 00009906 007.000.001 0x3A - EME/CCU - GWM_VCU1 - GWM VEHICLE CONTROL UNIT HWEL:9D3C-006.000.000 CAFD:9906-007.000.001_BTLD:B0CF-014.000.004_SWFL:B0E7-018.000.001_SWFK:B0E9-018.000.001 possible impact: Additional work in the production plant and the garage actions/steps to recover from error: - test case reference: VIT drive / FIT Fahrt Alexandru Tone, EA-PbM, 19.09.2023: Forward to GWM. 2023-09-19; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM.22.09.2023, C.Hauner, EC-EA-4:Duplikat zu1520413 -> blocking reason is set |  | 2023-09-18 16:17 | Julian Requejo | Theodora Papamina | Spotlight_FIT | D0105E - TA10027 |  | Appointment | CAFD:9906-007.000.001_BTLD:B0CF-014.000.004_SWFL:B0E7-018.000.001_SWFK:B0E9-018.000.001 | J01 | 0x23FF99 |  |  | J01 |  | Under Survey | 2023-10-05 11:09
GWM_VCU-01 | 1591734 |  |  |  |  | Multiple charging errors | GWM_VCU-01 | 01-New | 04-deficient | 02-sporadic | 2023091800227 | bmw | 0 | J001-23-11-520 |  |  |  | #PRIO# | Root cause : 1. AC charging at 18:38 12/09: As I checked yesterday, the EVSE changed the CP from 33% duty cycle to 100% duty cycle without any reason suddenly, it is just EVSE issue, and then the tester unplugged the cable from grid side for 2 times, finally the charging was normal. 2. DC charging at 12:11 14/09: This one is just you also checked that the e-lock reported an error and the vehicle reported CCM 802. then the tester re-plugged the cable, the charging was active normally. 3.DC charging at 14:47 14/09: This one is also e-lock error caused the vehicle reported CCM 802, then re-plugged the charging can be started normally. all the charging failed cases are not our EV issues the ticket can be rejected as EVSE / e-lock problem， confirmed by Sebastian | platform (e.g. BBG, FAT, TSP, Simulation,...): J01 PRODpreconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances):Vehicle was charged at several locations:- 12.09. AC Würzburg at 6:39pm- 14.09. DC Eon at 12:11pm- 14.09. HPC Eching 2:47pmexpected result/behaviour:Charging starts after connecting cable.observed result/behaviour:Several charging errors at different locations.possible impact:Customer irritated.actions/steps to recover from error:Disconnect cable and try again.test case reference:---Zeitpunkt:14.09.2023 [12:11:00] (UTC + 2), 0 km Melder:Dawidziuk Michael; EG-742; 382-77209; Michael.Dawidziuk@bmw.de Problemmanager: Ristikic Gabrijel; EG-741; ; Gabrijel.Ristikic@partner.bmw.de Fahrt(en):Von 12.09.2023 [08:00] Uhr, 15218 km bis 14.09.2023 [14:50] Uhr, 16472 km Fahrzeug:J01; EUR/DE; SE ; M-DI 971E; WMW21GC05RTA10013; B754022; 137169; I-Stufe:J001-23-11-520 Head Unit:MGU_02_A; BMW IDC23;pu2311-23w35.4-1-nodex_IDC23_E_23w35.4-1-3;idc23;HWEL:7D84-005.002.001 Ecu:GWM_VCU1; CAFD:9906-007.000.001_BTLD:B0CF-014.000.004_SWFL:B0E7-018.000.001_SWFK:B0E9-018.000.001; HWEL:9918-006.000.000 Map DB: / Equipment: Connected Drive:PROD: RemoteServices(RSVSR, RDL, VF_INTERNAL, R360_HU, RHL_INTERNAL, RD_INTERNAL, RLF, RDU, RHB, VF, RCN, RCHP, RCHC), GENERIC_VIN(MINI_PERSONAL_PICTURE, TRIP_STATISTICS, CRADIO, ANDROID_AUTO, SI_SMART_WINDOW_OPENER, APPS_PREMIUM, MEDIAENGINE, BMW_LINK_VIEWER, ON_STREET_PARKING, MAPS_DAILY_COMMUTE, AIRCONSOLE_IDC, MAPS_PREMIUM_POIS, MAPS_TRAFFIC_VISUALIZATION, MAPS_JUNCTION_VIEW, DCA_IDC_SERVICE, IP_LOCALIZATION, THIRDPARTYSTORE, MAPS_3D_VISUALIZATION, SPEECH_PREMIUM_VISUAL, PREMIUM_WELCOME_SCREEN, DPM_ISA, LBC_PARKING, SMACC_2_UWB_ANDROID, CARPLAY, DP_SMART_MAINTENANCE_VIS_D-OFF, PRIVACY_MANAGER, LOCATION_BASED_CHARGING_SETTINGS, CG_BASE_PLUS, SMART_ACCESS_BASIC, DISPLAY_OPTIMIZED_CHARGING, DRIVE_RECORDER_EXPORT, EUECALL, RSU_A4A, NONDORMANT, JOY_RECORDER, SMART_ACCESS_2_ACTIVATION_UWB, POI_SEARCH, RSU_BASIS, MAPS_ROW, EVENT_RECORDER, PARKNOW_POI, DR_NEXT_APP, SFA_MASTER, CRM_INFO, CDC_2018, AUTO_TIME_SERVICE, SAFE_SHARE_CAPABLE, SPEECH_THIRD_PARTY_ALEXASDK, MAPUPDATE_ADAS_L2, LSEARCH_APP_GOOGLE_LT, VWM_3_0, DCS, HV_WARN, IPA_BASE, MAPUPDATE_ADAS_L2_BASE, CRASH_RECORDER, ANDROID_WEATHER, SHOP, ANDROID_PROACTIVITY, MEDIA_COCKPIT, SAFETYCAM_IDC_SERVICE, PREMIUM_APP_THEME, SPEECH_CERENCE_LOCAL, SPEECH_CERENCE_CLOUD, AUGMENTEDVIEW_WIDGETACTIVATION, ASSISTEDDRIVINGVIEW_WIDGETACTIVATION, INCARPAYMENT, MY_HIGHLIGHTS_APP_IDC, SI_FESTIVAL_MODE, PERSO_GUESTPROTECT, FUTURE_DESTINATION, LBC_PARKING_RESERVATIONS), teleServices(RD_INTERNAL, LSC_OTD, ACALL_AUTOMATIC_MGU, MYINFO_INTERNAL, VF_INTERNAL, ACALL_MANUAL_MGU, TD_SPM, TD_B_CALL, RHL_INTERNAL, TD_TSBG, TD_ASC, TD_HOTLC), connectedDriveServices(FREETEXTSEARCH, MYINFO_PUSH, COUNTRY_INFO), intelligentEmergencyCall(PSAP, AACN), remoteServices(RSPP, RCN, VF, RLF, R360_HU, RSVSR, RDL, RCHC, RHB, RDU, RCHP), eMobilityServices(I_NATCHARGGST, LSC_PHEV) Traces:\\tcechdsmb.bmwgroup.net\brian-prod\EG-7_SP21_LU\J001\TA10013\20230915_0941\ Traces were converted with CARMEN 4.x TFC ==> please open the traces for analysis in CARMEN 4.x to get the correct timestamp Informationen zum Zugriff auf die referenzierten Traces TraceLab Session:https://tracelab.bmwgroup.net/sessions/vin/TA10013/timestamp/2023-09-14T12:11 VFC: Trigger:Nein GPS:50.027212, 12.117685 Anzahl aller Datei-Anhänge überschreitet das Octane Limit, deshalb wurden nicht alle Dateien ans Ticket angehängt. Traces/Daten sind in folgendem Verzeichnis verfügbar: \\tcechdsmb.bmwgroup.net\brian-prod\EG-7_SP21_LU\J001\TA10013\20230915_0941\ === end of error description === Alexandru Tone, EA-PbM, 18.09.2023: Forward to GWM. 2023-09-18; R.Prietzsch, EE-922, 01709826310 Rückmeldung Pbm: Handshake done by A.Tone. Ticket transfered to GWM.20.09.2023, C.Hauner, EC-EA-4:Reject announced, EVSE issue | Homologation L-labelled, No_Showstopper_Confirmed | 2023-09-15 12:59 | Julian Requejo | Michael Dawidziuk | [AT]FIT_LAENDER | WMW21GC05RTA10013 |  | Appointment | CAFD:9906-007.000.001_BTLD:B0CF-014.000.004_SWFL:B0E7-018.000.001_SWFK:B0E9-018.000.001 | J01 |  | 02-Integration |  | J01 | R-23-09 | Expected behaviour
GWM_VCU-01 | 1596279 |  |  |  |  | [J05][ENBN]Charging failed to start with charging station. (supplier company: TELD) | GWM_VCU-01 | 01-New | 05-unsatisfactory | 03-highly intermittend |  | bmw | 1 | J001-24-03-480 | [5 empty] | Platform (e.g. BBG, FAT, TSP, Simulation,...): J05-EnBn-CN-vehicle Vin: WMW81GC02PG000083 Software vision: GWM_VCU__01__21VCU800384G.017_000_009 Time：UTC+8 2023-9-16 13:24, 13:26 Supplier company: TELD City: Guangzhou Station: 广州市白云区鹤边和特来电充电站 Equipmenttype: DC Pile Number: 4401110074605 Tester contact information: Zhang, Yuning (Yuning.Zhang@partner.bmwgroup.com) Preconditions and actions (e.g. coding, route-url for navigation errors, weather/environmental circumstances): Preconditions: EVSEs in this charging station were tested, error only occurred in this EVSE.Is the failure occurred only once at target EVSE. 2 times occurred.SOC was 57% when error occurred. Actions: 1. Plug in the charger. 2. Start charging on the mobile phone app. Expected result/behaviour: 1. Charging starts. 2. The charging process runs without problems until it is actively terminated. Observed result/behaviour: 1. Charging was not start, "Charging aborted, charging station error" was shown in the HMI. 2. Action "stop the charging and recharge" 3. Charging was not start, "Charging aborted, charging station error" was shown in the HMI. possible impact: customer complain. actions/steps to recover from error: can not be recover. test case reference: no test case reference. === end of error description === Alexandru Tone, EA-PbM, 25.09.2023, 14:00 Uhr: Ticket should first be analysed from the Charging Station side, because: -ReasonChargingEnd = Fehler_außerhalb_des_Fahrzeugs; (from the traces) -"Charging aborted, charging station error" was shown in the HMI. (from the error description); -EVSEs in this charging station were tested, error only occurred in this EVSE. (also from the error description) | Homologation L-labelled | 2023-09-20 05:50 | Julian Requejo | Yuning Zhang | EnBn_IuA_CHN_Spotlight | 1 |  |  | GWM_VCU__01__21VCU800384G.017_000_009 | J05 |  |  |  | J05 |  | Not responsible